## Sprint Backlog
Sprint Backlog For: | Sprint 1
Sprint Backlog (By User Story) | Estimated Effort (person hours) | Team Member Responsible | Current Status (Drop down box) | Comments | Effort Remaining on Tasks - Update Daily
[5 empty] | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
[5 empty] | 2012-10-31 | 2012-11-01 | 2012-11-02 | 2012-11-05 | 2012-11-06 | 2012-11-07 | 2012-11-08 | 2012-11-09 | 2012-11-12 | 2012-11-13 | 2012-11-14 | 2012-11-15 | 2012-11-16
1. Whole Sprint Tasks |  |  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
Review feedback from Sprint 0 | 1 | Whole Team | Complete |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 1 Planning Meeting | 1 | JO | Complete | JO Scrum Master | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Consult with technicians regarding Android difficulties | 1 | JO | Complete | JO Scrum Master | bar: 2012-10-31 to 2012-11-16
Update GIT repository and resolve synchronisation issues | 2 | JO | Complete |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor Sprint 0 code where necessary | 5 | DCW | In Progress |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Research individual task | 10 | TT | In Progress |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  | JO | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | JO | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | JO | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. As a SHAREHOLDER I would like to see changes in stock price so that I can monitor my stock each day. |  |  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
Pair Programming - Test and Code | 5 | TT | In Progress |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Document Tests | 2 | DCW | In Progress |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Refactor | 5 | JO | Not Started |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  | TT | Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TT | Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TT | Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. As a SHAREHOLDER I would like to know the weekly high and low value of each share so that I can see how well they have performed. |  |  |  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
Pair Programming - Test and Code | 5 | JO | Not Started |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Document Tests | 2 | DCW | Not Started |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Refactor` | 5 | TT | Not Started |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  | JO | Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | JO | Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | JO | Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Effort Remaining | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Estimated Effort this sprint | 44 | hours
Progress Breakdown
Tasks Remaining | 7
Tasks in Progress | 4
Tasks Complete | 10

## Configuration Details
Sprint Start Date | 2012-10-31
Team Member Codes
JO | James
DCW | Ding Cong Wang (John)
TT | Theo
RS | Raj
Whole Team | Team